## Sheet1
TASKS | PRIORITY | DEADLINE | COMPLETE STATUS | PIC | DETAILED DESCRIPTION
MCU Selection | 1 |  | 100% | D & M | Select a MCU which satisfies the requirement of 1. numbers of Timers (PWM & Encoders) 2. integration of peripherials & middlewares(ADC USB) 3. wealth of learning materials 4. high performance & code porting
Driver Chip Selection | 1 |  | 100% | D & M | Select a driver chip which satisfies the requirement of 1. low drive voltage drop 2. small size & hign integration
USB protocol understanding | 1 |  | 100% | D | 1. USB master & slave 2. Several steps to recognize an USB device 3. It's relative circuit for USB 2.0
MCU HID setting | 1 |  | 100% | D | 1. Report descriptor 2. Send report function 3. Receive report function
RH MCU ADC setting | 1 | 2018-04-02 | 80% | D | 1. Frequency 2. DMA 3. Filter (not done)
RH MCU PWM setting | 1 |  | 100% | D | 1. cubemx setting 2. code implement
RH MCU Motor Class design | 1 |  | 100% | D | design a motor class for a more convenient way to control motor 1. enalbe & disable 2. PWM duty cycle setting 3. forward\backward\brake function 4 encoder & its relative function
RH MCU motion control | 1 | 2018-04-05 | 80% | D | 1. PID control function 2. PID parameter specification(not finished) 3. force application in motion control(not done) Qt work
RH PCB board testing | 1 | 2018-03-28 | 100% | D & M | 1. USB & SWD debugging circuit works well 2. ADC circuit(not test) 3. motor control(failed) 4 Encoder(not test)
Qt RH packe design | 2 | 2018-03-31 | 90% | D | build a union data structure for the communication of Matlab, MCU & Unity
Qt HID setting | 1 |  | 100% | D | Use a library of HID class for matlab mex file
Qt motion planning | 3 | 2018-04-07 | 0% | D | Smooth the motion trace (need a further consideration)
Qt socket setting | 4 | 2018-04-20 | 0% | D | Prepare a socket port for UNITY
Qt socket testing | 4 | 2018-04-20 | 0% | D & W
Qt GUI functions define | 5 | 2018-04-05 | 80% | D | define fuctions below: 1. HID device initilization, info sending, info reading. 2. Message building, Messeage processing. 3. Callback funtions for button.
Qt Gui ui design | 6 | 2018-04-20 | 30% | D | 1. design welcome page for connection info. 2.design the main page for PID setting and desired motion trace. 3. design the main page for dataglove (not decided)
Qt MCU testing | 4 | 2018-04-08 | 70% | D | 1. test its packet communication(finished) 2. test its msg building functions 3. test its msg processing functions(finished)
Qt MCU UNITY testing | 4 | 2018-04-10 | 0% | D & W | synchronize the virtual hand with dataglove.
Unity C# code understanding | 1 |  | 98% | W | 1. understand the sorce code of Unity. 2. learn about the control interface of each finger. 3. update the essential part for our project
Unity socket impletmentation | 1 | 2018-04-01 | 60% | W | 1. get an example of socket communication in C#. 2. try to modified its IP address & port for local setting. 3. merge the modified codes into your code.
Unity force feedback model construction | 2 | 2018-04-05 | 10% | W | 1. build a force feedback model in Unity. 2. Test it with the specified force. To WanZhong: Please give the detailed steps or description for constrcting the model.
Unity examplified game developing | 4 |  | 5 | W | To WanZhong: Please give what the examplified game is going to be.
RH V1 PCB Design | 1 |  | 100% | M | Design: 1. power supply module design 2. motor drive module design 3. ADC module design 4. MCU module design
RH V1 PCB Manufacture | 1 |  | 100% | M | Manufacture: 1. PCB 2. purchase electronic components 3. solding all the components
DG V1 PCB Design | 1 |  | 100% | M | Design: 1. power supply module design 2. EMG module design 3. ADC module design 4. MCU module design
DG V1 PCB Manufacture | 1 | 2018-04-06 | 90% | M | Manufacture: 1. PCB 2. purchase electronic components 3. solding all the components
RH V2 PCB Layout Design | 1 | 2018-03-28 | 100% | D & M & O | Design: 1. the solding pads 2. the sockets
RH V2 PCB Design | 1 | 2018-04-03 | 100% | M | Redesign-simpllification
RH V2 PCB Manufacture | 1 | 2018-04-15 | 50% | M | Manufacture: 1. PCB 2. purchase electronic components 3. solding all the components
DG Code Programming | 1 | 2018-04-06 | 60% | D & M | Code: 1. ADS1299 2. ADC
DG Code Testing | 1 | 2018-04-15 | 0% | D & M | 1. ADC 2. EMG signal
DG Manufacture | 1 | 2018-04-20 | 0% | M | 1. purchase raw materials 2. add sensors
RH inner transmission gear design | 1 |  | 100% | O | 设计传动件、出图、联系加工
RH 3D model modifying | 1 | 2018-04-01 | 100% | M & O | 机械手整体形状修改、完善内部细节 和马诗晗沟通确定PCB板具体形状和布置的位置
RH transmisiion gear manufacture | 2 | 2018-04-05 | 50% | O | 机械手内部其他需要机械加工的零件出图、联系加工
RH surface 3D printting | 3 | 2018-04-09 | 100% | O | 联系加工机械手3D打印的部分零件
RH alternate gears purchasing | 4 | 2018-04-13 | 0% | O | 寻找可以替代在加工的传动件的机械齿轮等部件用于测试的塑料齿轮（如冠齿轮）
RH standard parts purchasing | 5 | 2018-04-13 | 0% | O | 联系购买轴承、螺丝、传动带、扭簧等标准件